## Slide 1: Sprint Retrospective
Software engineering II
Politecnico di Torino, a. y. 2019/2020
Group F

## Slide 2
Stories and points
 | Total | Committed | Implemented
Stories | 9 | 5 | 3
Points | 26 | 19 | 12
- Number of hours per tasks: 0.9875

## Slide 3: Stories organization
Story Number | #Tasks
1 | 19
2 | 6
3 | 9
4 | 6
5 | 6
TOTAL | 46
Story Number | Actual Time | Estimated Time
1 | 19.5 ph | 18.5 ph
2 | 5 ph | 5.5 ph
3 | 8 ph | 8 ph
4 | 3 ph | 2 ph
5 | 5 ph | 2.5 ph
TOTAL | 32.5 ph | 32 ph
Estimation error ratio: 1.016
* only tasks implemented are considered in both times

## Slide 4: Task estimations: Story 1 (continued)
Task 1 |  | Task 2 |  | Task 3 |  | Task 4 | 
Actual | Estimated | Actual | Estimated | Actual | Estimated | Actual | Estimated
0.6 ph | 1 ph | 0.6 ph | 0.5 ph | 1 ph | 1 ph | 1 ph | 1 ph
Task 5 |  | Task 6 |  | Task 7 |  | Task 8 | 
Actual | Estimated | Actual | Estimated | Actual | Estimated | Actual | Estimated
1 ph | 1 ph | 2 ph | 1.5 ph | 2 ph | 1.5 ph | 0.5 ph | 1 ph

## Slide 5: Task estimations: Story 1 (continued)
Task 9 |  | Task 10 |  | Task 11 |  | Task 12 | 
Actual | Estimated | Actual | Estimated | Actual | Estimated | Actual | Estimated
0 ph | 0.5 ph | 0.6 ph | 0.5 ph | 1.5 ph | 0.5 ph | 0.75 ph | 0.75 ph
Task 13 |  | Task 14 |  | Task 15 |  | Task 16 | 
Actual | Estimated | Actual | Estimated | Actual | Estimated | Actual | Estimated
0.6 ph | 0.5 ph | 0.5 ph | 0.5 ph | 0.5 ph | 1 ph | 1 ph | 1 ph

## Slide 6: Task estimations: Story 1 (continued)
Task 17 |  | Task 18 |  | Task 19 | 
Actual | Estimated | Actual | Estimated | Actual | Estimated
1.5 ph | 1 ph | 2 ph | 1.5 ph | 2 ph | 1.5 ph
* 0 person hours means that we found out that the task was already implemented
in another one

## Slide 7: Task estimations: Story 2
Task 1 |  | Task 2 |  | Task 3 |  | Task 4 | 
Actual | Estimated | Actual | Estimated | Actual | Estimated | Actual | Estimated
0.5 ph | 0.6 ph | 0.4 ph | 0.5 ph | 0.6 ph | 1 ph | 0.5 ph | 1 ph
Task 5 |  | Task 6 | 
Actual | Estimated | Actual | Estimated
1.5 ph | 1.5 ph | 1.5 ph | 1 ph

## Slide 8: Task estimations: Story 3 (continued)
Task 1 |  | Task 2 |  | Task 3 | 
Actual | Estimated | Actual | Estimated | Actual | Estimated
0.5 ph | 0.4 ph | 0 ph | 0.5 ph | 1.5 ph | 1.5 ph
Task 4 |  | Task 5 |  | Task 6 | 
Actual | Estimated | Actual | Estimated | Actual | Estimated
0.5 ph | 1 ph | 0.6 ph | 0.5 ph | 0.5 ph | 0.5 ph

## Slide 9: Task estimations: Story 3 (continued)
Task 7 |  | Task 8 |  | Task 9 | 
Actual | Estimated | Actual | Estimated | Actual | Estimated
1.1 ph | 1 ph | 2 ph | 1.5 ph | 1.5 ph | 1 ph

## Slide 10: Task estimations: Story 4 and 5
We completed only half of tasks for both stories 4 and 5
The missing part is mainly testing and code review
Time spent and estimations are not reported because not useful for statistics (because incomplete)

## Slide 11: Story points comparison
 | Actual time | Estimated time
Story 1 (2p)* | 11.5 ph | 11 ph
Story 2 (2p) | 5 ph | 5.5 ph
Story 3 (8p) | 8 ph | 8 ph
 | Average actual time | Average estimated time
2-points stories | 8.25 ph | 8.25 ph
8-points stories | 8 ph | 8 ph
Ratio 2/8 | 1.031 | 1.031
* initial setup is not considered

## Slide 12: Wrong estimation reasons
  STORY ESTIMATION (story points)
    Story 1 with a lot of very simple tasks, better to consider an initial story ("Story 0") to include the starting configuration phase
    Story 3 with some features already implemented in previous stories, unlike initial ideas about related tasks (to each story)
  TASK ESTIMATION (person hours)
    Some tasks more trivial than expected, especially for background abilities
    Other tasks longer to implement, especially in integration testing
    Overall a balanced estimation, underestimation and overestimation in different tasks of the same story compensated each other

## Slide 13: Definition of Done
Unit test: well implemented on completed stories, but better to anticipate tests in the first stages, right after completion of related methods
Code review: better to schedule periodic face-to-face meeting instead of online remote checking, to integrate with online discussions
Use of VCS: repository constantly updated, few conflicts when merging
E2E test: better to start thinking about tests before design and implementation, to avoid too much code rewriting/refactoring

## Slide 14: Lessons learned
Negative:
  Bad organization of person hours among members can cause
  non-equal distribution of duties
  Too much work allocated close to the deadline lead to stress and lower quality code
  Not always complete participation of all members in team activities may lead to bad group decisions
Positive:
  Keeping track of files with a VCS makes it easier to work in team
  Scheduling of tasks before starting to code reduce the probability of overlapping
  Communication between all members of the team is the key to successful cooperation

## Slide 15: What to improve
  Correctly balance coding / testing tasks between members
  GUI improvement:
        Clearer elements inside the windows
        Content scalable with window dimensions

## Slide 16: We are proud of
  Use of ZenHub board to keep work organized and concise
  Tracking and organization of the group work progress
  Individual learning, new technical skills developed
  Well designed GUI for the ticket board application